Family Dashboard

SaaS Conversion Roadmap

dashboard.mccollumtechnology.com

Overview

This roadmap converts the Family Dashboard from a single-family local app into a multi-tenant SaaS product. Each Family Account is a fully isolated tenant with up to 8 member accounts, hosted at dashboard.mccollumtechnology.com via a Cloudflare tunnel from a home server, with Stripe handling subscriptions and license enforcement.

Architecture: Today vs. Target

| Dimension | Today | Target (SaaS) |
| --- | --- | --- |
| Auth | Google OAuth only | App-level signup + Google OAuth for calendar |
| Data | SQLite, single family | SQLite multi-tenant, family_id scoped everywhere |
| Access | Local network only | Public internet via Cloudflare tunnel |
| Payments | None | Stripe subscriptions, 14-day trial |
| Users | 1 family, unlimited members | Many families, up to 8 members each |
| Google App | Development / testing mode | Verified public app (OAuth consent screen) |
| Pi kiosk | Hard-coded localhost | Family API key in dashboard_config.json |

IMPORTANT: Google OAuth verification is the only externally-gated step (2-6 week review). Submit it in Week 1 and run everything else in parallel.

Phase 0 — Start Immediately: Google OAuth Public App  (Week 1)

Your app is in testing mode (100-user limit, scary unverified warning). Begin verification now — it is the only item gated on an external party.

Steps in Google Cloud Console

APIs & Services → OAuth consent screen

Switch from Internal to External

Fill in App name, logo, support email, developer contact email

Authorized domains: mccollumtechnology.com

Add scope: https://www.googleapis.com/auth/calendar.readonly

Link Privacy Policy: https://dashboard.mccollumtechnology.com/privacy

Link Terms of Service: https://dashboard.mccollumtechnology.com/terms

Credentials → OAuth 2.0 Client IDs

Add redirect URI: https://dashboard.mccollumtechnology.com/api/auth/callback

Keep a separate client ID for localhost dev

Submit for Verification

Record a 1-3 min demo video showing the OAuth flow and calendar data usage

Justify each sensitive scope in the submission form

Expect 2-6 week review; up to 100 test users allowed while waiting

Prerequisites Before Submission

Privacy Policy page live at a public URL

Terms of Service page live at a public URL

mccollumtechnology.com verified in Google Search Console (add DNS TXT record via Cloudflare)

support@mccollumtechnology.com email alias set up

Phase 1 — Infrastructure  (Week 1-2)

Cloudflare Tunnel

Add mccollumtechnology.com to your Cloudflare account (or confirm it is there)

Install cloudflared on the home server:

curl -L https://pkg.cloudflare.com/cloudflare-main.gpg | sudo apt-key add -

sudo apt install cloudflared

cloudflared tunnel login

cloudflared tunnel create family-dashboard

Create ~/.cloudflared/config.yml:

tunnel: <tunnel-id>

credentials-file: /home/user/.cloudflared/<tunnel-id>.json

ingress:

- hostname: dashboard.mccollumtechnology.com

service: http://localhost:80

- service: http_status:404

In Cloudflare DNS: add CNAME  dashboard  ->  <tunnel-id>.cfargotunnel.com  (proxied)

Enable as system service: cloudflared service install

Cloudflare provides free SSL termination, DDoS protection, WAF, and rate limiting at edge

nginx Reverse Proxy

Install nginx on the home server

Serve the built React frontend as static files from /opt/dashboard/frontend-dist

Proxy /api/ to uvicorn on port 8001

Use $http_cf_connecting_ip header to get real visitor IP from Cloudflare

Home Server Hardening

Block all inbound ports on the router — Cloudflare tunnel handles external access

Install fail2ban for SSH brute-force protection

Enable unattended-upgrades for automatic OS security patches

Set up hourly SQLite backups synced to Backblaze B2 (~$0.006/GB/month)

Phase 2 — Multi-Tenant Database & Architecture  (Week 2-4)

This is the core technical work. Every table gets a family_id column and every query is scoped to it. A FastAPI dependency extracts family_id from the JWT and injects it into every route.

New Tables

-- Tenant table

families (id, name, slug, plan, trial_ends, stripe_customer_id,

stripe_subscription_id, created_at)

-- Members within a family (replaces UserPrefs)

family_members (id, family_id, email, display_name, role,

invite_token, invite_expires, joined_at,

google_email, access_token, refresh_token, token_expiry)

-- Family-level config (replaces dashboard_config.json file)

family_config (family_id, config_json)

Isolation Rule

Every query that touches user data must include WHERE family_id = ?. Build a FastAPI Depends() that extracts family_id from the validated JWT and passes it to every route. Never trust a client-supplied family_id.

App-Level Authentication Strategy

| Option | Effort | Pros | Cons |
| --- | --- | --- | --- |
| Clerk (recommended) | ~2 days | Handles signup, login, invites, MFA, social login, user dashboard — no auth code to write | Third-party dependency; free tier ~500 MAU |
| Auth0 | ~3 days | Enterprise grade, generous free tier | More complex setup than Clerk |
| Build it yourself | ~2 weeks | No dependency, full control | Lots of code: bcrypt, JWT, invite tokens, password reset, session management |

Member Invitation Flow

Family admin enters email address in settings

Backend creates family_members row with invite_token UUID, sends invite email

Member clicks link -> https://dashboard.mccollumtechnology.com/invite/<token>

Member signs up or logs in -> account linked to family

Cap enforced: COUNT of joined members must be < 8 before generating invite

Pi Kiosk Device Tokens

display.py currently hits localhost with no auth. In the SaaS version each Pi must be associated with a specific family account. Add a device_api_key to the families table and store it in dashboard_config.json on the Pi. display.py sends it as a header on every API call.

Phase 3 — Payments & Licensing  (Week 3-5)

Stripe Account Setup

Create account at stripe.com with your real business information

Provide SSN or EIN (required for 1099-K at $600+ annual revenue)

Connect a bank account for payouts

Enable Stripe Tax to auto-calculate/remit sales tax ($0.50/transaction — optional but saves headaches)

Product & Pricing

Create Product: "Family Dashboard"

Create Prices:

$8.00/month  (recurring monthly)

$80.00/year  (recurring annual — 2 months free discount)

14-day free trial, no credit card required (best B2C SaaS conversion)

Enable Stripe Customer Portal (hosted billing self-service — zero code)

Enable Stripe Checkout (hosted payment page — no PCI scope on your server)

Webhook Events to Handle

| Stripe Event | Action |
| --- | --- |
| checkout.session.completed | Create family record, set plan = active |
| customer.subscription.updated | Sync plan status, update trial_ends |
| customer.subscription.deleted | Set plan = cancelled, lock API access |
| invoice.payment_failed | Set plan = past_due, send dunning email |
| invoice.paid | Renew subscription period, send receipt |

License Enforcement Middleware

Every FastAPI request goes through a dependency that checks family.plan. Allowed plans: active, trial (within trial_ends). All other plans return HTTP 402. This single middleware protects all API routes.

Phase 4 — Onboarding Flow  (Week 4-6)

Signup -> Payment -> Setup Sequence

/signup        Create account (email+password or Google SSO)

Create Family, set plan=trial, trial_ends=now+14d

/onboarding    Enter family name

Connect first Google account (calendar OAuth)

Invite up to 7 more members via email

/subscribe     Stripe Checkout (prompted at trial expiry)

/dashboard     Main app

Key UX Principles

No credit card required at signup — reduces friction dramatically

Show a countdown banner when < 5 days remain on trial

Invite link page shows a dashboard screenshot/preview to motivate sign-up

Family admin sees a member list with status: invited / active / removed

Member count badge: "3 / 8 members" always visible in settings

Phase 5 — Legal & Compliance  (Week 1, in parallel)

These documents are required before Google verification submission and Stripe activation. Write them in Week 1 using a generator (iubenda, termly) or AI assistance.

| Document | Required By | Key Contents | URL |
| --- | --- | --- | --- |
| Privacy Policy | Google, Stripe, GDPR | What data you collect, how Google calendar data is used, retention policy, deletion rights | /privacy |
| Terms of Service | Google, Stripe | Subscription terms, cancellation policy, acceptable use, limitation of liability | /terms |
| Cookie Policy | GDPR (EU users) | Session cookies, any analytics | /cookies |
| Data Deletion | Google OAuth policy | Must provide DELETE /api/account endpoint and UI button that wipes all family data | Settings page |

GDPR Considerations

If you have EU users: implement right to access (export family data) and right to erasure

Add DELETE /api/families/me endpoint that purges all family data from the database

Do not store Google calendar event content longer than necessary

Google requires a working data deletion link on the OAuth consent screen

Phase 6 — Hardening & Operations  (Week 5-7)

Rate Limiting

Install slowapi (pip install slowapi) — wraps FastAPI with per-IP limits

Limit: signup endpoint to 5 requests/min per IP

Limit: API overall to 100 requests/min per family

Limit: invite endpoint to 10/hour per family

Google Calendar API Quota Management

Per-project limit: 1,000,000 queries/day (generous)

Per-user limit: 10 requests/second (can be hit with polling)

Solution: cache calendar responses in SQLite with a 60-second TTL per family

display.py already polls every 60 seconds — ensure backend caches, not re-fetches

Database Backups

Cron job every hour: sqlite3 dashboard.db ".backup /backup/dashboard-$(date +%Y%m%d%H%M).db"

Sync backups to Backblaze B2 with rclone (~$0.006/GB/month)

Retain: hourly for 48h, daily for 30 days, monthly for 1 year

Test restore procedure before launch

Monitoring

| Tool | Purpose | Cost |
| --- | --- | --- |
| Sentry | Error tracking, stack traces, alerts on exceptions | Free tier (5K errors/month) |
| UptimeRobot | External uptime checks, SMS/email alert if site is down | Free tier (50 monitors) |
| Cloudflare Analytics | Traffic, threat blocking, bandwidth | Free (included with tunnel) |

Transactional Email

Required for: invite emails, trial expiry warnings, payment receipts, password reset

Recommended provider: Resend (resend.com) — simple API, 3,000 free emails/month

Install: pip install resend

Set up: support@mccollumtechnology.com as sender address

Add SPF and DKIM DNS records in Cloudflare for email deliverability

What You're Missing

Items most commonly overlooked until they become urgent problems:

Transactional email provider: You cannot send invite/welcome/payment emails without one. Gmail will get you blocked for bulk sending. Use Resend or SendGrid before any users sign up.

Google Search Console domain verification: You must verify mccollumtechnology.com in Google Search Console before the OAuth consent screen submission is accepted. Takes 10 minutes — add a TXT record in Cloudflare DNS.

Stripe tax handling: If charging US customers in states with digital services sales tax (NY, TX, WA, etc.), you may have a nexus obligation. Stripe Tax ($0.50/transaction) auto-calculates and remits. Consult a tax advisor if revenue grows.

Account deletion / data portability: Google's OAuth verification policy requires you to let users delete their data. Build DELETE /api/account and a visible "Delete my account" button before submitting for verification — Google reviewers look for this.

Pricing page: Stripe Checkout handles the payment flow, but you need a public /pricing page before people sign up. This is also where you A/B test monthly vs. annual pricing.

Pi kiosk device association: display.py currently has no auth. Each Pi must be associated with a family via a device API key in dashboard_config.json. Without this, any Pi could call any family's API.

Support channel: Even a simple support@mccollumtechnology.com alias forwarded to your inbox. Required for Google verification (they check). Builds user trust. Prevents silent churn.

Business structure: Consider forming an LLC before accepting payment. Protects personal assets, makes taxes cleaner, and is required by some payment processors for higher volumes.

Efficiency & Better Experience Ideas

| Idea | Effort | Value |
| --- | --- | --- |
| Clerk for authentication | Low (~2 days) | Eliminates ~2 weeks of auth code. Handles invites, MFA, social login, and a user management dashboard out of the box. |
| Stripe Billing Portal | Near zero | Customers manage their own cards, cancellations, and invoices. Eliminates "how do I cancel" support tickets entirely. |
| Annual pricing with discount | Zero | Offer $80/year vs $96/year (2 months free). Dramatically improves cash flow and reduces monthly churn. |
| 14-day trial, no credit card | Low | Best practice for B2C SaaS. Higher signup conversion. Add card prompt only at trial expiry. |
| Pre-flashed Pi SD card bundle | Medium | Sell a pre-configured SD card for $15-20 alongside the SaaS subscription. Family API key pre-loaded. Additional revenue stream + simpler onboarding. |
| Invite page with dashboard preview | Low | Show a screenshot or live demo of the dashboard when someone opens an invite link. Reduces invite-to-signup drop-off. |
| Feature flags column on families table | Low | A features JSON column lets you enable beta features per account or create plan tiers without code deploys. |
| Resend for transactional email | Low (~1 hour) | Dead simple API (one function call to send), best deliverability for small senders, 3,000 free emails/month. |
| Structured logging with family_id | Low | Add family_id to every log line. Essential for debugging multi-tenant issues and answering support tickets. |

Recommended Additional Tech Stack

| Component | Tool | Install / Notes |
| --- | --- | --- |
| Authentication | Clerk (managed) or python-jose + bcrypt (self-managed) | clerk.com or: pip install python-jose bcrypt |
| Email | Resend | pip install resend |
| Payments | Stripe | pip install stripe |
| Error monitoring | Sentry | pip install sentry-sdk |
| Uptime checks | UptimeRobot | Free external monitoring at uptimerobot.com |
| Database backups | sqlite3 + rclone + Backblaze B2 | rclone sync to B2 bucket |
| Rate limiting | slowapi | pip install slowapi |
| Tunnel | cloudflared | Already planned |

Suggested Timeline

| Week | Focus |
| --- | --- |
| Week 1 | Cloudflare tunnel live and domain resolving. Google OAuth verification submitted. Privacy Policy + Terms of Service written and published. Google Search Console domain verified. |
| Weeks 2-3 | Multi-tenant DB schema. Family and member models. FastAPI auth middleware with family_id scoping. |
| Weeks 3-4 | Stripe account setup. Webhook handler. License enforcement middleware. Pi device API key support. |
| Weeks 4-5 | Signup and onboarding flow. Member invite system. Transactional email with Resend. |
| Weeks 5-6 | Pricing page. Stripe Checkout integration. Stripe Customer Portal configuration. |
| Weeks 6-7 | Rate limiting. SQLite backups to B2. Sentry error monitoring. End-to-end hardening pass. |
| Weeks 7-8 | Beta test with your own family + 2-3 other families. Fix issues, gather feedback. |
| Week 8+ | Google verification approved (timeline permitting). Soft public launch. |

Start Google verification in Week 1. Everything else is in your control. The verification queue is the only item you cannot accelerate.